## Slide 1: Timeline for Noc 2019-2025 strategic plan
Sept. 5-save-the-date invitations sent to all employees and external stakeholders for town hall meetings.
Sept. 12-email sent with assessment survey to review mission, vision, core values, and initial list of goals. (deadline for return-sept. 26]
Oct. 3-strategic plan taskforce convenes (need volunteers for this and for subcommittees)
Oct. 10-email sent to share needs assessment survey results with all employees
  Oct. 29-noc Stillwater town hall meeting [3:00-5:00]
  Nov. 5-Noc tonkawa town hall meeting [3:00-5:00]
  Nov. 12-noc enid town hall meeting [3:00-5:00] [Nov. 27]
Nov. 28 [Nov. 30]-town hall notes are compiled and shared via email with all employees for further comment.
Jan. 16-strategic plan taskforce convenes to review all employee input and to identify subcommittees.
Jan. 29-taskforce presents draft of strategic plan to executive council.
Feb./march—subcommittees meet to develop action plans, including timelines and resources needed.
March 28 [April 10]—taskforce meets to finalize draft to present to all employees and noc board in april.